## Schedule Draft
Owl=0030-0830,Day=0830-1630,Eve=1630-0030 | [23 empty] | Fine Granularity (hour) | [7 empty] | Legend
Shift |  |  |  | Cyclotron | BL2A |  | ISAC | [8 empty] | OLIS | [6 empty] | Comments
|  |  |  | Offline | Offline | current (uA) | Exp. # | Facility | Note | West/ East | Beam | Energy (keV) | Tgt. | Source | Mod | Offline | Exp. # | Facility | Note | Beam | Energy (keV) | Source |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Examples of 3-letter codes for fine granularity operations
Tue | Oct | 10 | Owl | Shutdown | [11 empty] | Shutdown | [15 empty] | DEV = Development
|  |  | Day | Shutdown | [11 empty] | Shutdown | [15 empty] | OTR = Operator Training
|  |  | Eve | Shutdown | [11 empty] | Shutdown | [15 empty] | TBM = Target Block Move
Wed | Oct | 11 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Startup |  |  | Startup |  | <30kV | West |  |  | HPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve | Production |  |  | Startup |  | <30kV | West |  |  | HPTa | SIS/RILIS | 2 | Shutdown
Thu | Oct | 12 | Owl |  |  |  | Startup |  | <30kV | West |  |  | HPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  |  |  | Setup | LASER | <30kV | West |  |  | HPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  |  |  | Setup | LEBT | <30kV | West |  |  | HPTa | SIS/RILIS | 2 | Shutdown
Fri | Oct | 13 | Owl |  |  |  | Setup | YIELD | <30kV | West |  |  | HPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  |  |  | S1716 | GRIFFIN | <30kV | West | 72,74Ga |  | HPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  |  |  | S1716 | GRIFFIN | <30kV | West | 72,74Ga |  | HPTa | SIS/RILIS | 2 | Shutdown
Sat | Oct | 14 | Owl |  |  |  | S1716 | GRIFFIN | <30kV | West | 72,74Ga |  | HPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  |  |  | S1716 | GRIFFIN | <30kV | West | 72,74Ga |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | TBD |  | TBD
|  |  | Eve |  |  |  | S1716 | GRIFFIN | <30kV | West | 72,74Ga |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | TBD |  | TBD
Sun | Oct | 15 | Owl |  |  |  | Setup | LASER | <30kV | West | 156,158,160Er |  | HPTa | SIS/RILIS | 2 |  | Setup | LEBT |  | TBD |  | TBD
|  |  | Day |  |  |  | Setup | YIELD | <30kV | West | 156,158,160Er |  | HPTa | SIS/RILIS | 2 |  | Setup | HEBT |  | TBD |  | TBD
|  |  | Eve |  |  |  | Setup | CSB | <30kV | West | 156,158,160Er |  | HPTa | SIS/RILIS | 2 |  | Setup | SEBT |  | TBD |  | TBD
Mon | Oct | 16 | Owl |  |  |  | Setup | CSB | <30kV | West | 156,158,160Er |  | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS |  | TBD |  | TBD
|  |  | Day |  |  |  | Setup | SEBT | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Eve |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
Tue | Oct | 17 | Owl |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Day | Beam Development |  |  |  |  | <30kV | West |  |  | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD |  | DEV | DEV | DEV | DEV | DEV | DEV | DEV | DEV
|  |  | Eve | Beam Development |  |  |  |  | <30kV | West |  |  | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD |  | DEV | DEV | DEV | DEV | OTR | OTR | OTR | OTR
Wed | Oct | 18 | Owl |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Day |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Eve |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
Thu | Oct | 19 | Owl |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Day |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Eve |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
Fri | Oct | 20 | Owl |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | S1750 | TIGRESS | Pilot | TBD |  | TBD
|  |  | Day |  |  |  | S1750 | TIGRESS | <30kV | West | 156,158,160Er | 784000 | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | 20Ne |  | MCIS | (OLIS Setup if TIGRESS OK)
|  |  | Eve |  |  |  | Setup | LEBT | <30kV | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | 20Ne |  | MCIS | TIGRESS Changeover
Sat | Oct | 21 | Owl |  |  |  | Setup | YIELD | <30kV | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | Setup | POL | <30kV | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | Setup | POL | <30kV | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | Setup | LEBT |  | 20Ne |  | MCIS | TIGRESS Changeover
Sun | Oct | 22 | Owl |  |  |  | M1760 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | HEBT |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | M1760 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | M1426 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 20Ne |  | MCIS | TIGRESS Changeover
Mon | Oct | 23 | Owl |  |  |  | M1426 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | M1426 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | M1771 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 20Ne |  | MCIS | TIGRESS Changeover
Tue | Oct | 24 | Owl |  |  |  | M1771 | BNMR/NQR | M1771 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 20Ne |  | MCIS | TIGRESS Changeover
|  |  | Day | Maintenance | [5 empty] | West |  |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | 15N |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | M1571 | BNMR/NQR | M1571 BNQR | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | Setup | LEBT |  | 15N |  | MCIS | TIGRESS Changeover
Wed | Oct | 25 | Owl |  |  |  | M1571 | BNMR/NQR | M1571 BNQR | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | Setup | HEBT |  | 15N |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | M1571 | BNMR/NQR | M1571 BNQR | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 15N |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | M1571 | BNMR/NQR | M1571 BNQR | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 15N |  | MCIS | TIGRESS Changeover
Thu | Oct | 26 | Owl |  |  |  | M1571 | BNMR/NQR | M1571 BNQR | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 15N |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | M1571 | BNMR/NQR | M1571 BNQR | West | 8Li/9Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 15N |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 15N |  | MCIS | TIGRESS Changeover
Fri | Oct | 27 | Owl |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | S1425 | DRAGON |  | 15N |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source | Oven Prep | 23Na |  | SURF | TIGRESS Changeover
|  |  | Eve |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source | Oven Prep | 23Na |  | SURF | TIGRESS Changeover
Sat | Oct | 28 | Owl |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source | Oven Prep | 23Na |  | SURF | TIGRESS Changeover
|  |  | Day |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source | Oven Prep | 23Na |  | SURF | TIGRESS Changeover
|  |  | Eve |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source | Oven Prep | 23Na |  | SURF | TIGRESS Changeover
Sun | Oct | 29 | Owl |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source | Oven Prep | 23Na |  | SURF | TIGRESS Changeover
|  |  | Day |  |  |  | M1401 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | Source |  | 4He |  | MCIS | TIGRESS Changeover
|  |  | Eve |  |  |  | M1354 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | LEBT |  | 4He |  | MCIS | TIGRESS Changeover
Mon | Oct | 30 | Owl |  |  |  | M1354 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | HEBT |  | 4He |  | MCIS | TIGRESS Changeover
|  |  | Day |  |  |  | M1354 | BNMR/NQR | M1743 BNQR | West | 8Li |  | HPTa | SIS/RILIS | 2 |  | Setup | SEBT |  | 4He |  | MCIS
|  |  | Eve |  |  |  | TEST | Op Training | <30kV | West | 7Li |  | HPTa | SIS/RILIS | 2 |  | TEST | TIGRESS |  | 4He |  | MCIS
Tue | Oct | 31 | Owl |  |  |  | TEST | Op Training | <30kV | West | 7Li |  | HPTa | SIS/RILIS | 2 |  | TEST | TIGRESS |  | 4He |  | MCIS
|  |  | Day | Maintenance | [12 empty] | TEST | TIGRESS |  | 4He |  | MCIS
|  |  | Eve |  |  |  | Startup |  |  | East |  |  | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 36Ar |  | MCIS
Wed | Nov | 1 | Owl |  |  |  | Startup |  |  | East |  |  | HPSiC | FEBIAD | 4 |  | Setup | LEBT |  | 36Ar |  | MCIS
|  |  | Day |  |  |  | Startup |  |  | East |  |  | HPSiC | FEBIAD | 4 |  | Setup | HEBT |  | 36Ar |  | MCIS
|  |  | Eve |  |  |  | Setup | LEBT |  | East | 14O |  | HPSiC | FEBIAD | 4 |  | Setup | SEBT |  | 36Ar |  | MCIS
Thu | Nov | 2 | Owl |  |  |  | Setup | YIELD |  | East | 14O |  | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Day |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Eve |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
Fri | Nov | 3 | Owl |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Day |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Eve |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
Sat | Nov | 4 | Owl |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Day |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Eve |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
Sun | Nov | 5 | Owl |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Day |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | TEST | TIGRESS |  | 36Ar |  | MCIS
|  |  | Eve |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 23Na |  | SURF
Mon | Nov | 6 | Owl |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 23Na |  | SURF
|  |  | Day |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | Setup | LEBT |  | 23Na |  | SURF
|  |  | Eve |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | Setup | HEBT |  | 23Na | 105417 | SURF
Tue | Nov | 7 | Owl |  |  |  | S1140 | GRIFFIN |  | East | 14O | 55 | HPSiC | FEBIAD | 4 |  | Setup | SEBT |  | 23Na | 105417 | SURF
|  |  | Day | Maintenance | [5 empty] | East |  |  | HPSiC | FEBIAD | 4 |  | TEST | EMMA | Count | 23Na | 105417 | SURF |  | DEV | DEV | DEV | DEV | DEV | DEV | DEV | DEV
|  |  | Eve | Beam Development | [5 empty] | East |  |  | HPSiC | FEBIAD | 4 |  | TEST | EMMA | Count | 23Na | 105417 | SURF |  | DEV | DEV | DEV | DEV | OTR | OTR | OTR | OTR
Wed | Nov | 8 | Owl |  |  |  | Setup | YIELD |  | East | 24Na |  | HPSiC | FEBIAD | 4 |  | TEST | EMMA | Count | 23Na | 105417 | SURF
|  |  | Day |  |  |  | Setup | SEBT |  | East | 24Na | 115000 | HPSiC | FEBIAD | 4 |  | TEST | EMMA | Pilot | 23Na | 105417 | SURF
|  |  | Eve |  |  |  | TEST | EMMA |  | East | 24Na | 115000 | HPSiC | FEBIAD | 4 |  | TEST | EMMA | Pilot
Thu | Nov | 9 | Owl |  |  |  | TEST | EMMA |  | East | 24Na | 115000 | HPSiC | FEBIAD | 4 |  | TEST | EMMA | Pilot
|  |  | Day |  |  |  | TEST | EMMA |  | East | 24Na | 115000 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 15N |  | MCIS
|  |  | Eve |  |  |  | TEST | EMMA |  | East | 24Na | 115000 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 15N |  | MCIS
Fri | Nov | 10 | Owl |  |  |  | TEST | EMMA |  | East | 24Na | 115000 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 15N |  | MCIS
|  |  | Day |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | Setup | LEBT |  | 15N | 15300 | MCIS
|  |  | Eve |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | Setup | HEBT |  | 15N | 15300 | MCIS
Sat | Nov | 11 | Owl |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Day |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Eve |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
Sun | Nov | 12 | Owl |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Day |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Eve |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
Mon | Nov | 13 | Owl |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Day |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Eve |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
Tue | Nov | 14 | Owl |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Day | Beam Development | [5 empty] | East |  |  | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Eve |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
Wed | Nov | 15 | Owl |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Day |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | S1762 | DRAGON |  | 15N | 15300 | MCIS
|  |  | Eve |  |  |  | Devel | YIELD |  | East | 15O | 30 | HPSiC | FEBIAD | 4 |  | Setup | LEBT |  | 15N | 15300 | MCIS
Thu | Nov | 16 | Owl |  |  |  | Devel | YIELD |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | HEBT |  | 15N | 15300 | MCIS
|  |  | Day |  |  |  | Setup | HEBT |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 23Na |  | SURF
|  |  | Eve |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | LEBT |  | 23Na |  | SURF
Fri | Nov | 17 | Owl |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | POL |  | 23Na | 40 | SURF
|  |  | Day |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
|  |  | Eve |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
Sat | Nov | 18 | Owl |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
|  |  | Day |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
|  |  | Eve |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
Sun | Nov | 19 | Owl |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
|  |  | Day |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
|  |  | Eve |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
Mon | Nov | 20 | Owl |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | S1596 | POL |  | 23Na | 40 | SURF
|  |  | Day |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 12C |  | MWIS
|  |  | Eve |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 12C |  | MWIS
Tue | Nov | 21 | Owl |  |  |  | TEST | TUDA |  | East | 15O | 15300 | HPSiC | FEBIAD | 4 |  | Setup | Source |  | 12C |  | MWIS
|  |  | Day | Maintenance | [12 empty] | Setup | LEBT |  | 12C |  | MWIS
|  |  | Eve |  |  |  | Startup |  | <30kV | West |  |  | LPTa | SIS/RILIS | 2 |  | Setup | HEBT |  | 12C |  | MWIS
Wed | Nov | 22 | Owl |  |  |  | Startup |  | <30kV | West |  |  | LPTa | SIS/RILIS | 2 |  | Setup | SEBT |  | 12C | 114000 | MWIS
|  |  | Day |  |  |  | Startup |  | <30kV | West |  |  | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS |  | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | Setup | LASER | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS |  | 12C | 114000 | MWIS
Thu | Nov | 23 | Owl |  |  |  | Setup | LEBT | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS |  | 12C | 114000 | MWIS
|  |  | Day |  |  |  | Setup | YIELD | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS |  | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | Setup | SEBT | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Fri | Nov | 24 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Sat | Nov | 25 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Sun | Nov | 26 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Mon | Nov | 27 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Tue | Nov | 28 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day | Beam Development |  |  |  |  | <30kV | West |  |  | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS |  | DEV | DEV | DEV | DEV | DEV | DEV | DEV | DEV
|  |  | Eve | Beam Development |  |  |  |  | <30kV | West |  |  | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS |  | DEV | DEV | DEV | DEV | OTR | OTR | OTR | OTR
Wed | Nov | 29 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Thu | Nov | 30 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Fri | Dec | 1 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Sat | Dec | 2 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Sun | Dec | 3 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
Mon | Dec | 4 | Owl |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Day |  |  |  | S1506 | IRIS | <30kV | West | 12Be | 114000 | LPTa | SIS/RILIS | 2 |  | S1506 | IRIS | Pilot | 12C | 114000 | MWIS
|  |  | Eve |  |  |  | Setup | LEBT | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | [7 empty] | ISAC II OFF
Tue | Dec | 5 | Owl |  |  |  | Setup | YIELD | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2
|  |  | Day | Maintenance |  |  |  |  | <30kV | West |  |  | LPTa | SIS/RILIS | 2 |  | Setup | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | Setup | POL | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Wed | Dec | 6 | Owl |  |  |  | Setup | POL | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | M1770 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | M1770 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Thu | Dec | 7 | Owl |  |  |  | M1770 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | M1424 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | M1760 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Fri | Dec | 8 | Owl |  |  |  | M1760 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | M1760 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | M1760 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Sat | Dec | 9 | Owl |  |  |  | M1760 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | M1760 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | M9999 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Sun | Dec | 10 | Owl |  |  |  | M9999 | BNMR/NQR | M1606 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | M9999 | BNMR/NQR | M1674 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | M9999 | BNMR/NQR | M1674 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Mon | Dec | 11 | Owl |  |  |  | M1759 | BNMR/NQR | M1674 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | M1759 | BNMR/NQR | M1674 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | M1759 | BNMR/NQR | M1674 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Tue | Dec | 12 | Owl |  |  |  | M1759 | BNMR/NQR | M1674 BNQR | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day | Maintenance | [5 empty] | West |  |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Wed | Dec | 13 | Owl |  |  |  | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Day |  |  |  | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
|  |  | Eve |  |  |  | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 |  | TEST | Source | Op. Train. | 16O |  | MWIS | ISAC I Operator Training
Thu | Dec | 14 | Owl |  | Dump | 10 | TEST | YIELD | <30kV | West | 82gRb |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  | Dump | 10 | TEST | LEBT | <30kV | West | 82gRb |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  | Dump | 10 | TEST | FRANCIUM | <30kV | West | 82gRb |  | LPTa | SIS/RILIS | 2 | Shutdown
Fri | Dec | 15 | Owl |  | Dump | 10 | TEST | FRANCIUM | <30kV | West | 82gRb |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
Sat | Dec | 16 | Owl |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
Sun | Dec | 17 | Owl |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
Mon | Dec | 18 | Owl |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
Tue | Dec | 19 | Owl |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day |  | Dump | 10 | S1183 | MTV/OSAKA | <30kV | West | 8Li |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve |  | Dump | 10 |  |  |  | West |  |  | LPTa | SIS/RILIS | 2 | Shutdown
Wed | Dec | 20 | Owl |  | Dump | 10 |  |  |  | West |  |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day | Beam Development | [5 empty] | West |  |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Eve | Beam Development | [5 empty] | West |  |  | LPTa | SIS/RILIS | 2 | Shutdown
Thu | Dec | 21 | Owl |  | Dump | <2 |  |  |  | West |  |  | LPTa | SIS/RILIS | 2 | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Fri | Dec | 22 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Sat | Dec | 23 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Sun | Dec | 24 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Mon | Dec | 25 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Tue | Dec | 26 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Wed | Dec | 27 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Thu | Dec | 28 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Fri | Dec | 29 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Sat | Dec | 30 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown
Sun | Dec | 31 | Owl | Shutdown | [11 empty] | Shutdown
|  |  | Day | Shutdown | [11 empty] | Shutdown
|  |  | Eve | Shutdown | [11 empty] | Shutdown

## Stats - 8 hour shifts
8 hour shifts
%
Total Shifts Cyclotron | 251
Total Cyc Offline | 52
Shutdown | 36
Total Development or Maintenance | 16 | 7.442%
Total Cyc Available | 199
Total ISAC Available | 179
Startup | 9 | 5.028%
Setup | 25 | 13.97%
BNMR/NQR | 43 | 24.02%
TEST | 25 | 13.97%
Experiment | 77 | 43.02%
Setup/Experiment |  | 17.24%